## status
SR No | Application | Auditee comment | Timelines | Accepted | Comment | owner | Ph No. | status | Revalidation
1 | iHelpDesk | Done | Done | Yes | Requested for time - 31 oct 4 Nov - Followed ::resp-will by EOD 5 Nov - Again follwed (EOD) 7 Nov - Call this guy 20 Nov: Accepted XSS. 22 Nov: Got response and time for all. | Sandeep Jena | +91 40-41015613 | sent
2 | FCRM | Done | Done | Yes | finalization required for xss | Siva Pulavarthi | +91 40-41073032 | sent | 9 Jan: Requsted for the call (Org report by VED) 16 Jan: Followed up (internal clash)
3 | CMSWEB | No | Done | Yes | App lay off. Requested for response - 31 oct. Called and asked for time. | Vaibhav Shinde | +91 22-30437017 | sent
4 | Direct Banking Tracker |  |  | No Response | Requested - 31 oct Followed - 4 Nov | Ganesh Gosavi | +91 22-40093210 | sent
5 | Employee Loan Repayment | Done | Done | Yes |  | Srishti Mishra | +91 40-41065022 | sent
6 | eReconcialation |  |  |  | Sent report on 4-Nov | Adapureddy Kiran | +91 40-41011024 | sent
7 | FX NOOP | wait |  |  | call this guy 7 Nov - accepted to give comment and time. | Anwesh Neerati | +91 40-41011083 | sent
8 | LOP | wait |  | yes | Requested - 31 Oct Called - 4 Nov - finalized | Madhu Kumar | +91 40-41014068 | sent
9 | New CMART |  |  |  | Worked for 2 days Requested - 31 Oct Call scheduled on 2nd week-Nov 12 Nov - Walkthrough call. Asked for uploadDocument.jsp and access to app. 14 Nov - got access. Rqstd for URL and jsp file 18 Nov: Credds not working. Requested 9 Dec: Sent report | Amit Kumar | +91 40-41014090 | sent
10 | SMS Gateway |  |  | Waiting for response. | 11 Nov - Call her. Told, by EOD 12 Nov - Got updated code. 13 Nov - Code shared was old code again. Rqstd for new one. 14 Nov - Sent revised observation report. 21 Jan: sql and file upload. | Yamini Valety | +91 40-61012085 | sent
11 | FRS_Regulatory_Reporting-United_Kingdom |  |  |  | no observation 28 Nov: Sent mail as no observation. |  |  | done.
12 | iValue |  |  |  | no observation 28 Nov: Sent mail as no observation. | Paritosh Kumar | +91 22-30437141 | done.
13 | ICICI_Financial_Data_Warehouse |  |  |  | no observation 28 Nov: Sent mail as no observation to Gira Trivedi. | KIRAN Chavan | +91 22-33887204 | done.
14 | WBG-Credit Monitoring Dashboard |  |  |  | No Code 16 Jan: Sent report | Sreedhar Karimi | +91 40-41061516 | no
15 | DFS (Dealer Funding System) |  |  |  | aspx not given properly Ask for proper aspx 4 Nov - walkthrough req 6 Nov - requested for proper code. Postpone review. 11 Nov - followed up. Hesitant to share code. Reqtd yet n sur. - sent mail to everyone and asked yet for assistance. | Shanka Chakrabartty | +91 40-41014083 | no
16 | LAMS |  |  |  | no codebehind files ask for codebehind 4 Nov - walkthrough req sent 6 Nov - called and requested 7 Nov - app owner requested for scope 11 Nov - ask manasa for codebehind 28 Dec: Requested for walkthrough 31 Dec: Sent report | Srikanth Aduri Manasa Gaddam | 40-41012058 40-41012059 | no
17 | ICICI Application Integration |  |  |  | 12 Nov - Sent observation report | Avadh Gupta | +91 22-50116618 | Sent
18 | Channel Financing System |  |  |  | 11 Nov - Requested for codebehind. 27 Nov: Got some codebehind files. Started review | Avirup Das | +91 40-41014099 | Sent
19 | NRISR (NRI Speed Remittances) |  |  |  | 18 Nov: Started NRISR review. Ask for call tomorrow. 19 Nov: Requested for walkthrough 20 Dec: Accepted all except query string. SQL Injection need to be checked again. | Kumar Anand | +91 40-41012305 | Sent | 301987
20 | Money2India |  |  |  |  | Karthik Vankadari | +91 40-41012605 | Sent
21 | E-Settlemen System |  |  |  | 18 Nov: Whole code in all CRs. Requested for modular code. 21 Nov, 05 Dec, 09 Dec: Followed up. Agreed to send on 12 Dec 17 Dec: Got 3CR code at 6pm. 18 Dec: Completed review on 3 CRs. | vishwanath.devarakonda | +91 40-41061032
22 | CSGL |  |  |  | 13 Nov - Requested for walkthrough. -They shared full code in 4 CRs out of 5 14 Nov - Sent mail saying it takes a lot of time to review whole code and to share code in CRs. RESPONSE: Dear Naveen, Sneha is on leave till coming Monday and will be able to respond to you on Tuesday. [[[19 Nov]]] 16 Dec: Sent report. 19 Dec: Had discussion over 45 mins. Accepted everything except weak password policy. GAVE REASON FOR THE SAME. | G Snehasri | +91 40-41065095 | Sent
23 | EAI |  |  |  | 13 Nov: Only biztalk. 18 Nov: Requested for call today. | Premsagar Boddireddy | +91 40-41084240 | Sent | BAN47883
24 | CAR (Customer Authentication Relationship) |  |  |  | 3 Dec: Requested for walkthrough 4, 5 Dec: Followed up 10 Dec: Again followed 16 Dec: Again requested. Escalated to Yetendera | MADHU | +91 40-41012098 |  | 303763
25 | Retail Mobile Banking Canada |  |  |  | 10 Jan: Code shared by suresh.
26 | Retail Mobile Banking UK
12 Nov - Sent list of apps for which proper code is needed to Suresh
| Sent observation. Awaiting. |  |  |  | 121/2, 13 n 14 - spent on sms gateway
In Progress.
Finished everything.
Delay and waiting for something

## Roadmap
SR No. | Application Name | Lines of Code | Estimated time | Remarks | Target Date | Actual End Date | Reason for delay
1 | SMS Gateway | 155253 | 5 |  | 2019-10-30 | 2019-10-23
2 | Direct Banking Tracker | 52021 | 1 | Already worked 4 days on it | 2019-10-30 | 2019-10-21
3 | iValue | db scripts | 2 |  | 2019-10-22 | 2019-10-25
4 | ICICI Financial Data Warehouse | db scripts | 2 |  | 2019-11-24 | 2019-10-24
5 | eReconciliation | 95 + db scripts | 2 |  | 2019-11-24 | 2019-11-04
6 | EAI (Enterprise Application Interface) | 18308 | 3 |  | 2019-11-24 | 2019-11-21
7 | CSGL | 526811 | 6 |  | 2019-11-24 |  | 13 Nov: Whole code has been given in 4 out of 5 CRs. Requested for modular code. RESPONSE: Dear Naveen, Sneha is on leave till coming Monday and will be able to respond to you on Tuesday. [[[19 Nov]]]
8 | DFS (Dealer Funding System) | 37186 | 4 |  | 2019-12-08 |  | Needed proper code. So, not started
9 | E-Settlement System | 612308 | 8 |  | 2019-12-08 |  | Whole code in all CRs
10 | ICICI Application Integration | 65980 | 4 |  | 2019-12-08 | 2019-11-12
11 | New CMART | 18898 | 3 |  | 2019-12-08 | 2019-11-29 | walkthrough delayed till 2nd week of nov
12 | Source Code Review - LAMS | 2778 | 2 |  | 2019-12-08 |  | No codebehind.
13 | WBG-Credit Monitoring Dashboard |  |  | Waiting for proper CR code from application team |  |  | No Code
14 | CFS (Channel Financing System) | 17508 | 2 |  | 2019-01-10 | 2019-12-03 | No Codebehind. 26 Nov: got codebehind on 5:30PM
15 | Money2India |  |  |  | 2019-01-10 | 2019-11-29
16 | NRISR (NRI Speed Remittances) |  |  |  | 2019-01-10 | 2019-11-21
17 | CAR |  |  |  | 2019-01-10
18 | iHelpDesk
19 | FCRM
20 | CMSWEB
21 | Employee Loan Repayment
22 | FX NOOP
23 | LOP
24 | FRS Regulatory Reporting- United Kingdom

## Requirements
sr no. | application | Requirement
1 | LAMS | Codebehind files for given aspx files
2 | Dealer Funding System | proper .aspx and a.spx.cs files
3 | Channel Financing System | Codebehind files for given .aspx files.
4 | WBG Credit Monitoring Dashboard | Proper code need to be shared as CRs.

## Observatiopns
SR No. | Vulnerability | Application | Severity
| Unrestricted File Upload | CMSWEB NRISR (NRI Speed Remittances) SMS Gateway (Short Messaging Service Gateway) WBG-Credit Monitoring Dashboard | High
| SQL Injection | iHelpDesk CSGL DFS (Dealer Funding System) E-Settlement System Money2India NRISR (NRI Speed Remittances) SMS Gateway (Short Messaging Service Gateway) | High
| XML Entity Expansion (Billion Laughs Attack) | iHelpDesk NRISR (NRI Speed Remittances) | High
| Stored Cross-Site Scripting (XSS) | CFS (Channel Financing System) | High
| Reflected Cross-Site Scripting | iHelpDesk FCRM DFS (Dealer Funding System) Direct Banking Tracker E-Settlement System ICICI Application Integration Money2India | Medium
| Cross-Site Request Forgery | FCRM LOP (Loan On Phone) ICICI Application Integration | Medium
| Possible SQL Injection | FX NOOP CAR DFS (Dealer Funding System) eReconciliation | Medium
| Link Injection | FCRM | Medium
| Log Injection | CMSWEB iHelpDesk FCRM Money2India New CMART NRISR (NRI Speed Remittances) | Medium
| Missing or Broken Authorization Mechanism | iHelpDesk | Medium
| Formula Injection | CSGL DFS (Dealer Funding System) LAMS (Logical Access Management System) WBG-Credit Monitoring Dashboard | Medium
| ASP.NET Debugging Enabled | CSGL
| Mail Injection | LAMS (Logical Access Management System) | Medium
| DOM-Based Cross-Site Scripting | New CMART | Medium
| Temporary Password Sent In Clear Text Over Email | NRISR (NRI Speed Remittances)
| Unsalted Password Hashes | NRISR (NRI Speed Remittances)
| Weak Hash Function | NRISR (NRI Speed Remittances)
| Sensitive Data Stored in Log Files(password) | NRISR (NRI Speed Remittances)
| Improper Resource Shutdown | CMSWEB iHelpDesk Employee Loan Repayment System FCRM FX NOOP CAR CSGL DFS (Dealer Funding System) Direct Banking Tracker E-Settlement System ICICI Application Integration Money2India New CMART NRISR (NRI Speed Remittances) SMS Gateway (Short Messaging Service Gateway) WBG-Credit Monitoring Dashboard | Low
| Possible Reflected Cross-Site-Scripting (XSS) | CMSWEB | Low
| Weak Input Validation | CMSWEB FCRM DFS (Dealer Funding System) Direct Banking Tracker E-Settlement System LAMS (Logical Access Management System) Money2India SMS Gateway (Short Messaging Service Gateway) | Low
| Sensitive Data Stored in Log Files | iHelpDesk DFS (Dealer Funding System) | Low
| Autocomplete HTML Attribute Not Disabled for Sensitive Fields | FCRM NRISR (NRI Speed Remittances) | Low
| Query String Parameter in HTTPS Request | iHelpDesk FCRM FX NOOP Direct Banking Tracker E-Settlement System ICICI Application Integration Money2India NRISR (NRI Speed Remittances) | Low
| Information Leakage via Code Comments | Employee Loan Repayment System LOP (Loan on Phone) CAR CSGL SMS Gateway (Short Messaging Service Gateway) WBG-Credit Monitoring Dashboard | Low
| Cacheable HTTPS Content | FCRM | Low
| Security Misconfiguration | LOP (Loan on Phone) CFS (Channel Financing System) Direct Banking Tracker LAMS (Logical Access Management System) | Low
| User IDs and/or Passwords Hardcoded in Source Code | CAR ICICI Application Integration SMS Gateway (Short Messaging Service Gateway) WBG-Credit Monitoring Dashboard | Low
| Cacheable HTTPS Content | E-Settlement System New CMART
| Empty Password | SMS Gateway (Short Messaging Service Gateway)
| HTTPS Not Enforced | iHelpDesk LOP (Loan on Phone) Direct Banking Tracker ICICI Application Integration SMS Gateway (Short Messaging Service Gateway) | N/A

## Accurate_status
Sr. No. | Application Name | Completed CR |  | Source Code Receive (Yes/No) | Verfiied Source code (Yes/No) | Completion Target Date | Start Date | Completion/Query send shet Date | Technology | CR Count | Observation Found |  |  |  | Current Status
|  | Major | Minor | [7 empty] | High | Medium | Low | Total
1 | CFS (Channel Financing System) |  | 16 | Yes | Yes | January 10, 2020 | November 23, 2019 | December 03, 2019 | .Net, SQL | 5 | 1 | 0 | 1 | 2 | Completed
2 | CMSWEB |  | 43 | Yes | Yes | September 04, 2019 | August 23, 2019 | September 04, 2019 | Java | 5 | 1 | 3 | 1 | 5 | Completed
3 | DFS (Dealer Funding System) |  | 14 | Yes | Yes | January 10, 2020 | December 31, 2019 | January 07, 2020 | Java | 5 | 1 | 4 | 2 | 7 | Completed
4 | Direct Banking Tracker | 3 | 4 | Yes | Yes | October 21, 2019 | September 22, 2019 | October 21, 2019 | .Net | 5 | 0 | 1 | 4 | 5 | Completed
5 | EAI (Enterprise Application Interface) | 5 | 37 | Yes | Yes | November 24, 2019 | November 13, 2019 | November 21, 2019 | Biztalk | 5 | 0 | 0 | 0 | 0 | Completed
6 | E-Settlement System | 1 | 53 | Yes | Yes | December 8, 2019 | December 06, 2019 | December 20, 2019 | .Net | 5 | 1 | 1 | 4 | 6 | Completed
7 | FCRM | 1 | 45 | Yes | Yes | September 11, 2019 | August 29, 2019 | September 11, 2019 | Java | 5 | 0 | 3 | 6 | 9 | Completed
8 | FX NOOP |  | 8 | Yes | Yes | September 24, 2019 | September 16, 2019 | September 24, 2019 | .Net | 5 | 0 | 1 | 2 | 3 | Completed
9 | ICICI Application Integration |  | 46 | Yes | Yes | November 12, 2019 | November 04, 2019 | November 12, 2019 | Java, SQL | 3 | 0 | 2 | 3 | 5 | Completed
10 | iHelpdesk |  | 49 | Yes | Yes | September 5, 2019 | August 22, 2019 | September 5, 2019 | Java | 5 | 2 | 4 | 0 | 6 | Completed
11 | iValue | 5 | 14 | Yes | Yes | October 22, 2019 | October 21, 2019 | October 22, 2019 | SQL | 5 | 0 | 0 | 0 | 0 | Completed
12 | LOP (Loan on Phone ) |  | 24 | Yes | Yes | September 16, 2019 | September 11, 2019 | September 16, 2019 | .Net | 5 | 0 | 1 | 1 | 2 | Completed
13 | FRS Regulatory Reporting- United Kingdom |  | 2 | Yes | Yes | October 09, 2019 | October 7, 2019 | October 09, 2019 | .Net | 1 | 0 | 0 | 0 | 0 | Completed
14 | Employee Loan Repayment System |  | 2 | Yes | Yes | October 09, 2019 | August 22, 2019 | October 09, 2019 | .Net | 2 | 0 | 0 | 2 | 2 | Completed
15 | SMS Gateway |  | 10 | Yes | Yes | October 23, 2019 | October 14, 2019 | October 23, 2019 | .Net | whole | 2 | 0 | 6 | 8 | Completed
16 | CSGL |  | 10 | Yes | Yes | November 25, 2019 | November 29, 2019 | December 16, 2019 | .Net | 5 | 1 | 3 | 2 | 6 | Completed
17 | WBG-Credit Monitoring Dashboard |  | 16 | Yes | Yes | January 10, 2020 | January 03, 2020 | January 16, 2020 | Java | 5 | 1 | 1 | 3 | 5 | Completed
18 | New CMART |  | 26 | Yes | Yes | December 08. 2019 | November 04, 2019 | December 09, 2019 | Java | 5 | 0 | 2 | 2 | 4 | Completed
19 | ICICI Financial Data Warehouse | 10 | 14 | Yes | Yes | October 24, 2019 | October 23, 2019 | October 24, 2019 | SQL | 5 | 0 | 0 | 0 | 0 | Completed
20 | eReconciliation |  | 17 | Yes | Yes | November 04, 2019 | October 23, 2019 | November 04, 2019 | SQL | 5 | 0 | 1 | 0 | 1 | Completed
21 | LAMS (Logical Access Management System) |  | 21 | Yes | Yes | January 15, 2020 | December 26, 2019 | December 31, 2019 | .Net | 5 | 0 | 2 | 2 | 4 | Completed
22 | NRISR (NRI Speed Remittances) | 2 | 23 | Yes | Yes | January 18, 2020 | November 12, 2019 | November 21, 2019 | Java | 5 | 3 | 5 | 3 | 11 | Completed
23 | CAR (Customer Authentication Relationship) | 6 | 56 | Yes | Yes | January 10, 2020 | December 04, 2019 | January 16, 2020 | Java | 5 | 0 | 1 | 3 | 4 | Completed
24 | Money2India | 3 | 119 | Yes | Yes | January 10, 2020 | November 25, 2019 | November 29, 2019 | Java | 5 | 1 | 1 | 3 | 5 | Completed
25 | SmartForm-CA |  | 6 | No | No | [9 empty] | Pending
26 | Retail Mobile Banking Canada |  | 7 | No | No | February 7, 2020 | January 22, 2020 | February 07, 2020 | ios, android, java | 5 | 0 | 3 | 3 | 6 | Completed
27 | Retail Mobile Banking UK |  | 1 | No | No | February 7, 2020 | February 2, 2020 | February 07, 2020 | Java | 1 | 0 | 1 | 0 | 1 | Completed
28 | iMobile IBMWorklight |  | 26 | No | No | [9 empty] | Pending
29 | Corporate Tablet Banking application (iBizz HD) |  | 2 | No | No | [9 empty] | Pending

## Sheet2
SR No
1 | Give us whole code so that review can be done effectively,.
2 | Proper tools need to be provided(like visual studio, internet access, burp suite etc)
3

## Actual_dates
CAR | 2020-08-09
CFS(Channel_Financing_System) | 2020-08-09
CMSWEB | 2020-08-09
CSGL | 2020-08-09
Direct_Banking_Tracker | 2020-08-09
EAI(Enterprise Application Interface) | 2020-08-09
Employee_Loan_Repayment_System | 2020-08-09
eReconciliation | 2020-08-09
FCRM | 2020-08-09
FRS_Regulatory_Reporting-United_Kingdom | 2020-08-09
FX_NOOP | 2020-08-09
ICICI_Financial_Data_Warehouse | 2020-08-09
iHelpdesk | 2020-08-09
iValue | 2020-08-09
LOP | 2020-08-09
SMS_Gateway | 2020-08-09
WBG-Credit_Monitoring_Dashboard | 2020-08-09
DFS (Dealer Funding System) | 2020-12-05
E-Settlement System | Oct
ICICI Application Integration | Oct
imobile | 2020-02-05
Money2India | 2020-10-17
New CMART | Oct
NRISR (NRI Speed Remittances) | 2020-11-04
Retail Mobile Banking Canada | 2020-01-10
Retail Mobile Banking UK | 2020-01-29